## Project Details & Sheet_list
Facility Name | FULL SITE NAME
Site Address
Center Manager
Implementation Engineer | Anthony J
PRJ# | PRJ00xxxxx
READING GROUP | CONNEXIA
TAX ID | xx-xxxxx
Site Code | xxxxx
NPI | xxxxxxxxxx
Site Visit dates | Initial site visit | During NW Go live for setup/config | During IT hardware Go live | During Clinical Go live | For overall proj GL
IT Procurement (Order & Delivery)
Circuit Order date |  | Circuit Delivery date |  | Circuit Install date
Network Infra equipment order date |  | Network Infra equipment Delivery date |  | Network Infra equipment install/config date
End User devices order date |  | End User devices Delivery date |  | End User devices setup date
Modalities Order Date |  | Modalities Delivery Date |  | Modalities setup/config Date
Phones order date |  | Phones Delivery date |  | Phones setup date
Card Readers order date |  | Card Readers Delivery date |  | Card Readers setup/config date
Network Go-Live Date |  | 2026-06-15
IT Hardware Go-Live Date |  | 2026-07-13
Clinical Go-Live Date |  | 2026-07-20 |  | AHI IMG Centers
Site Go-Live Date |  | 2026-07-20 |  | Dynasoft Print Driver
Altamont 3.4
Clario
Vulkan shortcuts
SHEET LIST INDEX |  |  |  | Altamont shortcut
1. Project Details : Site name, address, GO live dates and other project info |  |  |  | AHI PACS Synapse
2. IT Timeline : overall timeline for the Project (each phase-wise from W1 to W16 timeline view) |  |  |  | zvext v4.4.2
3. Overall project plan : List of activities for each phase with action owner and start/end dates |  |  |  | AHI IMG Centers Manger
4. Technical procurement tracker : this is used for NW/IT/ modalities order, shipping info and other technical details |  |  |  | Batch Share Drive
5. TDR and checklist – for at the site before network and IT go live
6. GO live issue tracker – for issues post/during Go live and resolution

## Project Timeline-IT
IT Timeline | Month 0 | Month 1 |  | Month 2 |  | Month 3 |  |  |  | Month 4 |  |  |  | Hypercare Support
Phase/Workstream activities |  | W1 to W2 | W2 to W4 | W5 to W6 | W7 to W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
| 16 Feb-03Apr | 06-17 Apr | 20Apr-01 May | 04-15 May | 18-29 May | 01-05 Jun | 08-12 Jun | 15-19 Jun | 22-26 Jun | 29 Jun-03 July | 06-10 July | 13-17 July | 20-24 July | 27 - 31 July | 03 - 07Aug
Construction (Permit / Circuit) |  | Month 1 W1 to W2: Construction Starts; Month 4 W15: Construction Ends
Contracting (TCO, Vendor contract) |  | Month 1 W1 to W2: Circuit Order; Month 2 W7 to W8: Circuit Delivery
TCO, HLD
IT data Closet Readiness?
Floor Plan, Equipment, Low Voltage | Floor Plan, Biz ops request
Low Voltage
[6 empty] | SDWAN order | SDWAN delivery & setup
Order & Procurement | CT ordered (end of feb) | Month 3 W12: CT Delivery; Month 4 W13: CT calibration & Install
Infrastructure | MRI ordered (end of feb) | Month 3 W10: MRI Delivery (Tent)
| US ordered? | Month 4 W14: US Delivery (Tent)
Modalities |  | Month 2 W5 to W6: NW equipment ordered? Switches/cables?
|  |  | End User Hardware ordered? | [7 empty] | IT hard ware setup/ install & accesses provided
Telecom/Phones |  | Month 3 W9: Phones Order (6-8weeks prior to IT Go live); Month 4 W14: Phone Delivery (to check w/ VOIP) to be delivered before IT Go live
|  |  | Card Readers ordered? | [7 empty] | card reader setup & access
Hardware/ Infra Installation |  | Month 3 W9: Network/ Infra equipment setup, Config & install
Network Go Live |  | Month 3 W11: NETWORK GO LIVE (21days after IT closet is ready)
|  |  |  | other Modalities ordered? (If reqd) |  |  |  | Modalities testing and readiness Modalities GO Live
PACS Implementation |  | Month 3 W12: PACS Implementation (6 weeks prior to Go Live - based on IPs)
RIS Implementation |  | Month 3 W12: RIS Implementation
HL7 |  | Month 3 W12: HL7 Implementation
Revenue Cycle |  | Month 3 W12: Revenue Cycle
Testing and training |  | Month 4 W16: Testing (& w/live patients) and Training; Hypercare Support W17: Additional Training (if reqd)
IT Harware GO Live |  | Month 4 W15: IT Hardware Go Live
Clinical Apps Go live |  | Month 4 W16: Clinical Apps Go Live (first patient)
Project Go-Live |  | Month 4 W16: Overall Project GO live (site opened)
Project Closure |  | Hypercare Support W17: Project Closure Documentation
Hypercare & handover to HCL for Support |  | Hypercare Support W17: Handover to HCL for support
LEGEND
NOT STARTED
COMPLETED
ORDER
DELIVERY
MODALITIES
NETWORK/ INFRA
APPS IMPLEMENTATION, TESTING
Questions/clarification?
Site Walk through (1day?) - initial site walk through is optional - not mandatory
IT Order & Procurement (Date?) - based on DC readiness circuit order & NW infra order
VPN Tunnel (FW check)
Delivery (Date?) - ~1 week before IT Go live is scheduled

## Overall project plan
Sno | Activities list | STATUS | Action owner | Dependency | Start date/ Ordered date | End date/ Delivery date (at the site) | Comments/Notes
I | Phase 0 : Construction/ Facility Readiness and project initiation
1.1 | Execution of Lease | Complete | Regional IT Dir
1.2 | Issuance of permits | Complete | Regional IT Dir
1.3 | Approval from GEC | Complete | Regional IT Dir
1.4 | Idea to Demand request | Complete | Regional IT Dir
1.5 | Construction scheduled started | SCHEDULED | Construction PM |  | 2026-04-06 | 2026-07-13 | construction to be started on April 06
1.6 | Define Scope and project requirements
1.6a | TCO completion | Complete | IT OP Dir / PMO
1.6b | HLD and timelines | Complete | IT OP Dir / PMO
1.7 | IT Demand Submission to conversion and approval | Complete | IT OP Dir / PMO
1.8 | Circuit ordered | Not Started | IT OP Dir | start date of construction or permit recevied | 2026-04-06
1.9 | Contracting |  | Regional IT Dir
1.9a | Intelerad | IN Progress | Regional IT Dir
1.9b | FUJI | IN Progress | Regional IT Dir
1.9c | vendor contracts (licenses, if any reqd) | IN Progress | Regional IT Dir
1.1 | Project Governance |  | PMO
1.10a | Identify all stakeholders (Define PMO, Implementation team) | Complete | PMO |  |  |  | PMO, Implementation Engr
1.10b | Project initiation/ Kick off (Define PRJ number -PRJ00xxxxx) | Complete | PMO |  |  |  | Kick off call to started from 03/17
1.10c | Weekly/biweekly cadence - to be scheduled | IN Progress | PMO | w/all stakeholders |  |  | once in 2 weeks : calls scheduled with Ops team IT internal calls scheduled : for readiness & updates
1.10d | Define milestones, deliverables & project timelines | IN Progress | PMO |  |  |  | Project plan and milestones in progress
1.10e | Define GO live dates : Define IT Go live date, Network GO live dates & overall project Go live dates | IN Progress | PMO
| Checkpoint Deliverables : Finalize Project plan, risk trackers, all project documentation | IN Progress | PMO
1.11 | Pre-req/initial requirements
1.11a | Gather/Review site details and plans (Name of facility/center manager) | Complete | PMO/ implementation team
1.11b | RIS Site Code | Complete | PMO/ implementation team
1.10c | Get bit.ly | IN Progress | PMO/ implementation team
1.10d | Get Main and Fax number VOIP Engineer | Complete | PMO/ implementation team
1.10e | Get NPI / TAX ID - | Complete | PMO/ implementation team
1.10f | IP Address Requests | IN Progress | PMO/ implementation team
1.10g | Add location to Service Now | IN Progress | PMO/ implementation team
1.10h | Vendor Contracts (Intelerad, Volpara, Pacscan liscences, etc) and Comms w/SPOCS |  | PMO/ implementation team
i | Granite (for circuts/ SDWAN connection) | Not Started | IT OP Dir
ii | Momentum (for phones) | Not Started | VOIP Engineer (UIF for each location)
1.11i | Low Voltage call & Heat Map Review Floor plans (including millwork that could change IT setup), engage low voltage vendor, get approval of network drops from customern(ex. printer locations), make sure there is enough power for all equipment | Complete | Anthony with Ops team |  | 2026-02-02 | 2026-02-02 | Low voltage call completed on 02Feb, heat map also created (see technical procurement tracker)
Deliverables : Sign off Approvals for project requirements & plan
Project documentation (on teams including sign offs)
II | Phase 1 : IT Procurement & Ordering
2.1 | Initial Site walk through | Not Started | Implementation team/PMO
2.2 | Define Shipping plan (For NW/Infra, End user devices, modalities & Telecomm) | Not Started | Implementation team/PMO
2.2a | Get WAP plan from Granite, order WAPs | Not Started | IT OP Dir / implementation team
2.2b | Develop shipping plan for onsite equipment | Not Started
2.3 | Order & Delivery :Network/ Infrastructure
FALSE | Circuit/Fiber Primary DIA | Not Started | IT OP Dir
FALSE | Circuit/Fiber Secondary / BB | Not Started | IT OP Dir
FALSE | Circuit/Fiber Third - 300 | Not Started | IT OP Dir
FALSE | SDWAN Router - 7 days after Circuit Turned up | Not Started | Implementation team/PMO
FALSE | Switch | Not Started | Implementation team/PMO
FALSE | WAPs | Not Started | Implementation team/PMO
FALSE | VPN (for remote modality connection) | Not Started | Implementation team/PMO
FALSE | Low voltage cabling/fiber | Not Started | Implementation team/PMO
FALSE | UPS (rack mounted) | Not Started | Implementation team/PMO
FALSE | MOD server (if applicable) | Not Started | Implementation team/PMO
2.4 | Order & Delivery :End User Devices |  | Implementation Team
| Compile End User Equipment List and get sign off from customer on order | Not Started | Implementation Team
| Develop Revenue Cycle Plan | Not Started | Implementation Team
FALSE | Desktops Bundle (with dual monitors) | Not Started | Implementation Team
FALSE | Desktops Bundle (with single monitors) | Not Started | Implementation Team
FALSE | Laptop Bundle (with dual monitors and dock) | Not Started | Implementation Team
FALSE | Standard Monitors 24' | Not Started | Implementation Team
FALSE | Docking Station | Not Started | Implementation Team
FALSE | Reading Workstation | Not Started | Implementation Team
FALSE | iPad | Not Started | Implementation Team
FALSE | iPad MDM | Not Started | Implementation Team
FALSE | Office - document scanners | Not Started | Implementation Team
FALSE | ID scanners | Not Started | Implementation Team
FALSE | headset | Not Started | Implementation Team
FALSE | Webcam | Not Started | Implementation Team
FALSE | USB | Not Started | Implementation Team
FALSE | Card Readers – Orders 3-6 weeks out | Not Started | Vendor
FALSE | surge protectors | Not Started | Implementation Team
FALSE | Dell CD Burner | Not Started | Implementation Team
FALSE | Desktop Printers | Not Started | Implementation Team
FALSE | MFP | Not Started | Implementation Team
FALSE | Phone numbers, fax, ATA for outbound faxes | Not Started | Implementation Team
FALSE | Reading station (if applicable) | Not Started | Implementation Team
FALSE | 1’ blue patch cables | Not Started | Implementation Team
FALSE | Cable Management - order Raceway and clips | Not Started | Implementation Team
FALSE | 1’ red patch cables | Not Started | Implementation Team
FALSE | 1’ yellow patch cables | Not Started | Implementation Team
FALSE | 3’ grey Cat 8 cable | Not Started | Implementation Team
FALSE | 5’ white Cat 8 cable | Not Started | Implementation Team
FALSE | 10' Black Cables | Not Started | Implementation Team
2.5 | Order & Delivery : Modalities |  | Modality Apps
| Gather all Modality information, submit requests for IPs and DICOM info, delivery info and contacts | Not Started | Modality Apps
| order modalities(2 weeks prior to NW go live)- 2 weeks delivery timeline approx submit tickets and share RITM # w/PM, Modalities vendor : Hologix, GE, Seimens (is it BU wise? Construction PM shares info) | Not Started | Modality Apps
| workstation equipment if ready to be ordered for modalities (not for the site but only modalities) - Tech to submit separate tickets (lead time : TBD ) | Not Started | Modality Apps
FALSE | MRI 1 | SCHEDULED | Modality Apps |  |  |  | Regional IT Dir to order end of Feb on MRI & CT to be delivered by June - MRI 06/16 & CT 06/23
FALSE | MRI Remote | Not Started | Modality Apps
FALSE | MR Bayor Inj | Not Started | Modality Apps
FALSE | MRI 2 | Not Started | Modality Apps
FALSE | MRI Remote | Not Started | Modality Apps
FALSE | MR Bayor Inj | Not Started | Modality Apps
FALSE | CT | SCHEDULED | Modality Apps |  |  |  | Regional IT Dir to order end of Feb on MRI & CT to be delivered by June - MRI 06/16 & CT 06/23
FALSE | US 2 | Not Started | Modality Apps
FALSE | US 3 | Not Started | Modality Apps
FALSE | Xray | Not Started | Modality Apps
FALSE | R&F | Not Started | Modality Apps
FALSE | Bone Den | Not Started | Modality Apps
FALSE | MFP | TBD
2.4 | Order & Delivery :Phones |  | VOIP Engineer
| Develop Telecom Plan | Not Started | VOIP Engineer
FALSE | phones / Cordless Phones (Phone numbers) | Not Started | VOIP Engineer (Deliverables : UIF for phones)
FALSE | ATA (for outbound faxes) | Not Started | VOIP Engineer
FALSE | Go-Live of E-Fax | Not Started | VOIP Engineer
FALSE | Telecom | Not Started | VOIP Engineer
FALSE | Five9 | Not Started | VOIP Engineer
FALSE | PACE (IVR) | Not Started | VOIP Engineer | (For TMI & AHI, SJRA), new sites might not have PACE/Five9 UPMC - ?)
| Deliverables : Sign offs Approvals for all procurement UIF for phones for each location from Bron |  | VOIP Engineer
| all order documentation (on teams) |  | VOIP Engineer
III | Phase 2 : Installation and Infrastructure Configuration |  | PMO/ Implementation team
| Configure network equipment and determine shipping/install plan | Not Started | PMO/ Implementation team
| Circuits/ SDWAN network setup | Not Started | PMO/ Implementation team | Network Team
| Site visit walk through after delivery | Not Started | PMO/ Implementation team
| Low Voltage Network Cabling implementation checks | Not Started | PMO/ Implementation team
| End user devices installation | Not Started | PMO/ Implementation team
| Modalities installation & configuration | Not Started | PMO/ Implementation team | Modality Apps
| after NW is up - coordinate on testing for modalities | Not Started | PMO/ Implementation team
| after delivery at the site - based on confirmation of vendor/Tech on delivery at the site After NW go live is completed Modalities - schedule testing at the site (Implementation Team), FSO tech, HCL apps team (remote) - HCL creates the bridge to work on testing (1 day) PMO to provide confirmation to all stakeholders | Not Started | PMO/ Implementation team
| Phone setup & telecomm plan | Not Started | PMO/ Implementation team
| Printer setup | Not Started | PMO/ Implementation team
| Vendor VPN/ Remote support | Not Started | PMO/ Implementation team
| Comms and coordination with all vendors for installation & setup | Not Started | PMO/ Implementation team
| Checkpoint : Site visit and approvals on installation completion |  | PMO/ Implementation team
| Network GO Live Readiness (NW & IT Checklist, TDR to be completed & approved) |  | PMO/ Implementation team | network isto be ready and tested at least 15 days before go-live
| Network GO Live |  | PMO/ Implementation team
IV | Phase 3 : Application Implementation |  | Implementation / App team
| Application build - (FUJI PACS, Interlerad PACS, RIS, Clario, HL7) | Not Started | Kurt's team will perform the RIS build (RIS team)
| All Information Required to Create Site Name | Not Started | Core Informatics
| All Information Required to Create Site (Name, Site Code, Tax Info, Fax Info) | Not Started | Operations
| Site Build - Request needed (Test and Prod) - Scheduling Template | Not Started | Core Informatics, L2-RIS APPS
| Build Resources in RIS | Not Started | L2-RIS APPS
| Users Added (Site Handles this) (PACS, Clario, RIS if needed) | Not Started | Operations
| Interfaces (Site added to Interfaces Internal) test/prod | Not Started | Implementation Team
| Interfaces (Site added to Interfaces External if needed (Connexia)) test/prod | Not Started | Implementation Team
| Site to the PDF to DICOM convertor - Request Needed | Not Started | L2-Custom-Apps
| Build Inbound faxing (Ticket) | Not Started | L2-PACS Dication Apps
Clario
| Email to Clario team to let them know about the new site | Not Started | Implementation Team
| Verify Clario team has things built for testing | Not Started | Implementation Team
PACS Implementation
InteleRAD PACS
| Add modalities to PACS with AE Titles and names | Not Started | PACS Implementation Team
| Obtain list of procedures for the Xray equipment for protocols | Not Started | PACS Implementation Team
| Once modalities are in place, setup MWL | Not Started | PACS Implementation Team
| Ticket to add Ord Code to InteleRad | Not Started | PACS Implementation Team
| Ticket to Create Bins (should do a test order to give them an example) | Not Started | PACS Implementation Team
| Setup and Test work BINS | Not Started | PACS Implementation Team
| Get sheet ready for Modality Work list Vendor | Not Started | PACS Implementation Team
| Verify Users have been Trained | Not Started | PACS Implementation Team
| Role is to configure the MOD server in the data center and establish routing rules | Not Started | PACS Implementation Team
FUJI PACS
| Request Modalities to be built in PACS- Will Resources for MWL | Not Started | L2-PACS Dication Apps
| Test Modality Work list | Not Started | PACS Implementation Team
| Get sheet ready for Modality Work list Vendor | Not Started | PACS Implementation Team
| Verify Users have been Trained | Not Started | PACS Implementation Team
RIS Implementation
FUJI RIS
| Add site bins and test ahead of modalities | Not Started | RIS Implementation team
| Add paperwork to send from site to PACS | Not Started | RIS Implementation team
| Add new sites and org | Not Started | RIS Implementation team
| Add new users | Not Started | RIS Implementation team
| Coordinate w/ Scheduling | Not Started | RIS Implementation team
| Code MR as FastScan | Not Started | RIS Implementation team
| HL7 configuration & implementation | Not Started | HL7 interface team
Build/modify interfaces
Revenue Cycle
| credit card readers setup | Not Started | REV REC team
| Cleargage / ImaginePay | Not Started | REV REC team
| RIS Access | Not Started | REV REC team
| Interfaces | Not Started | REV REC team
| Deploy Card readers | Not Started | REV REC team
| Patient Engagement plan/implementation | Not Started | Health logix (only for AHI & TMI) not for CLT UPMC - ??
| Facility map link used in conjunction with Health logix patient engagement | Not Started | PMO/ Implementation team
| Deliverables : Site visit and approvals on app implementation completion |  | PMO/ Implementation team
V | Phase 4 : Testing Validation and Training |  | HCL Apps team
| RIS and PACS Testing validation | Not Started | HCL Apps team
| Verify Site Configurations (Logo,Image Launch URL, Faxing) | Not Started | HCL Apps team
| Verify Fast Scan times if applicable | Not Started | HCL Apps team
| End to End testing - (Schedule, Order, Begin, Images, Scan Paperwork, Complete, Sign, Addendum) | Not Started | HCL Apps team
| AutoRouting Rules if needed | Not Started | HCL Apps team
| Add routing rules if applicable | Not Started | HCL Apps team
| software installation, TVs online, software are installed & tested, E-fax testing | Not Started | HCL Apps team
| Modalities testing - IT PMO provides confirmation to all stakeholders | Not Started | HCL Apps team
| During overall project GO live - additional testing of images sent/connectivity working for modalities (1day) | Not Started | HCL Apps team
| Install and Complete IT on-site implementation Check-List | Not Started | PMO/ Implementation team
| Deliverables on Application Readiness : test all equipment and modalities, customer test and sign off approvals |  | PMO/ Implementation team
| IT GO Live Readiness (NW & IT Checklist, TDR to be completed & approved) |  | PMO/ Implementation team
| Review power plan and IT closet readiness, circuit vendor may require it to be completely ready for their installation | Not Started | PMO/ Implementation team
| IT GO Live |  | PMO/ Implementation team
VI | Phase 5 : Overall project Go live |  | PMO/ Implementation team
| Final Site walk thru and Approvals/Sign off | Not Started | PMO/ Implementation team
| Staff to be trained on phones (to be included in project plan- basic training) differs from site-to-site | Not Started | PMO/ Implementation team
| training will need be done on site GO -live : Day 1 when staff is on at the site or training to be given to the site manager | Not Started | PMO/ Implementation team
| Go live Readiness | Not Started | PMO/ Implementation team | equipment to be completely installed at least 5 business days in advance of go-live (for testing & troubleshooting)
| Send HCL DRAFT of Inventory - RITM Request - Email with RITM and Attachment –( email address) | Not Started | PMO/ Implementation team
| Schedule initial Project Transition meeting with HCL, complete and share draft documentation | Not Started | PMO/ Implementation team
| Install and test all equipment and modalities, customer test and sign off on application readiness Complete IT on-site implementation Check-List (to be created) | Not Started | PMO/ Implementation team
| Approvals from Capex team to proceed w/Go live | Not Started | PMO/ Implementation team
| Overall Go live |  | PMO/ Implementation team
VII | Project Closure |  | PMO / Implementation team
| Closure documentation | Not Started | PMO / Implementation team
| Overall Sign offs and Approvals from all stakeholders for project closure | Not Started | PMO / Implementation team
| Cost tracking & submit to Finance, IT leadership & Business | Not Started | PMO / Implementation team
VII | Hypercare Support and handover |  | PMO / Implementation team
| Finalize HCL Support Transition Documentation (workbook shared by HCL) | Not Started | PMO / Implementation team
| Document "lessons" learned and update documentation | Not Started | PMO / Implementation team
| Schedule training session with HCL for project handover documentation | Not Started | PMO / Implementation team
| 2 weeks of transitioning to HCL with hypcare / operations support provided | Not Started | PMO / Implementation team

## Technical procurement tracker1 (hidden)
Denovo Site : Type Information : IT Timeline | [14 empty] | Facility Name
Site Address
|  |  |  | 120 | 100 | 80 | 60 | 40 | 30 | 20 | 10 | 5 | Go-Live | Post Go-Live | Center Manager
|  | TCO | 120 days | [12 empty] | date of | date of | date of | date of | date of | date of | date of | date of
|  | Permit / Circuit | 120 Days | [11 empty] | Barriors
|  | Vendor Contract | 120 Days | [11 empty] | Barriors
|  | Floor Plan, Equipment, Low Voltage | 100 Days | [11 empty] | Barriors
|  | IP and Modality Info | 60 Days | [12 empty] | date of | date of | date of | date of | date of | date of | date of | date of
|  | Phone Plan | 60 Days | [11 empty] | Milestones
|  | Site Walkthrough | 45 Days | [11 empty] | Milestones
|  | Network Readiness | 30 Days | [11 empty] | Milestones
|  | IT / Modality Readiness | 15 Days | [12 empty] | Location Add | Equip Order | Phones | Card Readers |  | Network Equipment |  | RIS DocMWL / Fax
|  | TDR with End Users | 5 Days | [11 empty] | Incident Number
|  | Go-Live Issue Resolution | Week After | [19 empty] | Site Build
Site Blueprint
Product Owner | Quantity | Equipment Status | Items Ordered | Items Received |  | Modality Type | Connection Date | IP Address | Subnet | Gateway | DNS1 / DNS2 | Vendor | AE Title | DAS | MWL | Port | RITM Request | End to End Testing | Additional Note
Workstations |  | Desktops Bundle (with dual monitors) | FALSE | FALSE |  | CT | [11 empty] | FALSE
Workstations |  | Desktops Bundle (with single monitors) | FALSE | FALSE |  | MRI | [11 empty] | FALSE
Workstations |  | Laptop Bundle (with dual monitors and dock) | FALSE | FALSE |  | US | [11 empty] | FALSE
Workstations |  | Standard Monitors 24' | FALSE | FALSE |  | X-Ray | [11 empty] | FALSE
Workstations |  | Docking Station | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | Reading Workstation | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | iPad | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | iPad MDM | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | Canon imageFORMULA DR-C225 II Office - document scanner | FALSE | FALSE |  | Existing Equipment |  | IP Address | Subnet | Gateway |  | Vendor | AE Title
Workstations |  | Jabra Evolve 40 UC stereo headset | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | Logitech HD Pro Webcam C920S | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | Topaz SignatureGem LCD1x5 - signature terminal - USB | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | Card Readers - Cody orders 3-6 weeks out | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | Dell CD Burner | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | Desktop Printers | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | MFP | FALSE | FALSE | [8 empty] | MFP Model |  |  |  |  | FALSE
Workstations |  | 1’ blue patch cables | FALSE | FALSE |  | MFP | [11 empty] | FALSE
Workstations |  | Cable Management - order Raceway and clips | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | 1’ red patch cables | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | 1’ yellow patch cables | FALSE | FALSE |  | RIS | Site to PACS | RIS | RIS | PACS | [5 empty] | Network Go-Live Date
Workstations |  | 3’ grey Cat 8 cable | FALSE | FALSE |  | Add Site Bin | Paperwork | Add Site¦ Org | Add New Users | Site Filter |  | TAX ID |  |  |  | IT Go-Live Date
Workstations |  | 5’ white Cat 8 cable | FALSE | FALSE | [7 empty] | Site Code |  |  |  | Site Go-Live Date
[5 empty] | Ordered | Installed | Turned Up |  |  |  |  | NPI |  |  |  | HL Complete | HL Tested |  | IP Address | Subnet | Gateway | DNS1 | DNS2
Infrastructure |  | Circuit/Fiber Primary | FALSE | FALSE | [7 empty] | Health Logix | [5 empty] | VLAN 300
Infrastructure |  | Circuit/Fiber Secondary | FALSE | FALSE |  |  |  |  | Network Equip Specifics |  |  | Obtained IP | [5 empty] | VLAN 303
Infrastructure |  | SDWAN Router - 7 days after Circuit Turned up | FALSE | FALSE | [7 empty] | Meet with Center Mgr Date
Infrastructure |  | Switch | FALSE | FALSE |  | FALSE | Pete |  |  |  |  | Software Validated |  |  |  | Specialty Hardware |  |  | Software List
Infrastructure |  | WAPs | FALSE | FALSE |  | FALSE | Pete/Josh/Anthony |  |  |  |  | RIS / PACS Type
Infrastructure |  | VPN (for remote modality connection) | FALSE | FALSE |  | FALSE | Pete
Infrastructure |  | Low voltage cabling/fiber | FALSE | FALSE |  | FALSE | Josh/Anthony
Infrastructure |  | UPS (rack mounted) | FALSE | FALSE |  | FALSE | FSO |  |  |  |  | E-Fax Date
Phones |  | phones | FALSE | FALSE |  | FALSE | Bron |  |  |  |  | Main Number
Phones |  | ATA | FALSE | FALSE |  | FALSE | Bron |  |  |  |  | Inbound FAX
Fax |  | Go-Live of E-Fax |  |  |  |  | Bron

## To Do List (hidden)
DeNovo To Do List
Timing | Milestone | Task | Dependencies/ Notes
GEC Approval
Immediately after Capital Approval |  | IT Demand Submission
Immediately after Capital Approval |  | Communicate project & timeline to JV partner IT team (if applicable)
120 days out |  | TCO completion, approval move to active project
120 days out |  | Gather/Review site details and plans, define implementation team
120 days out |  | RIS Site Code email Kayce.Dunn@lumexaimaging.com or ” Mihai.Borodi@lumexaimaging.com
120 days out |  | Get bit.ly from Jessica Cloeter <jessica.cloeter@lumexaimaging.com>
120 days out |  | Get Main and Fax number from Bron Dutton <Bron.Dutton@lumexaimaging.com>
120 days out |  | Get NPI / TAX ID - Katrina.Roelle@lumexaimaging.com
120 days out |  | Add location to Servive Now
120 days out |  | Order Circuits
120 days out |  | Vendor Contracts (Intelerad, Volpara, Pacscan licenes, etc)
100-120 days out |  | Review Floor plans (including millwork that could change IT setup), engage low voltage vendor, get approval of network drops from customern(ex. printer locations), make sure there is enough power for all equipment
100-120 days out | IT Closet Readiness | Review power plan and IT closet readiness, circuit vendor may require it to be completely ready for their installation
100-120 days out |  | Order switch, SDWan, UPS and any other equipment needs for IT closet
100 -120 days out |  | Compile End User Equipment List and get sign off from customer on order
100-120 days out |  | Get WAP plan from Granite, order WAPs
60-90 days out |  | Gather all Modality information, submit requests for IPs and DICOM info, delivery info and contacts
60-90 days out |  | Request Health Logics
60-90 days out |  | Place equipment order
60-90 days out |  | Develop Telcom Plan
60-90 days out |  | Develop Revenue Cycle Plan
45-90 days out |  | Configure network equipment and determine shipping/install plan
45-90 days out |  | Initial Site Walkthrough? - Confirm IT Closet set up, set up network if circuit is installed
45-90 days out |  | Develop Patient Engagement Plan
45-90 days out |  | Develop Application build/implementation plan
45-90 days out |  | Request Card Readers from Cody
30-45 days out |  | Develop go-live support plan (secure onsite and remote resources)
15-30 days out | Network Readiness | Site walkthrough, set up and test network, if not done in initial walkthrough | If network is not ready and tested at least 15 days before go-live, should we push go-live?
15-30 days out |  | Develop shipping plan for onsite equipment
7-15 days out |  | Send HCL DRAFT of Inventory - RITM Request - Email with RITM and Attachment - HCLProjecthandover@usradiology.com
7-15 days out |  | Schedule initial Denovo Transition meeting with HCL, complete and share draft documentation
0-15 days out | Go-Live Readiness | Install and test all equipment and modalities, customer test and sign off on application readiness Complete IT on-site implementation Check-List (to be created) | If equipment cannot be completely installed at least 5 business days in advance of go-live, should we push go-live? We need at least 5 business days for testing and troubleshooting prior to go-live Reasons equipment could not be installed: Facility Readiness (ex. not clean, no COO, etc) Equipment not shipped on time or arrives broken/not configured
Post Go-Live
0-15 days after |  | Finalize HCL Support Transition Documentation
0-15 days after |  | Document "lessons" learned and update documentation
0-15 days after |  | Decomission old site/ equipment?

## Technical procurement trackerol (hidden)
BTDI Temple: Denovo : IT Timeline | [14 empty] | Facility Name
[15 empty] | Site Address | 605 S. Pea Ridge Road, Temple, TX 76502
|  |  |  | 120 | 100 | 80 | 60 | 40 | 30 | 20 | 10 | 5 | Go-Live | Post Go-Live | Center Manager
|  | TCO | 120 days | [12 empty] | date of | date of | date of | date of | date of | date of | date of | date of
|  | Permit / Circuit | 120 Days | [11 empty] | Barriors
|  | Vendor Contract | 120 Days | [11 empty] | Barriors
|  | Floor Plan, Equipment, Low Voltage | 100 Days | [11 empty] | Barriors
|  | IP and Modality Info | 60 Days | [12 empty] | date of | date of | date of | date of | date of | date of | date of | date of
|  | Phone Plan | 60 Days | [11 empty] | Milestones
|  | Site Walkthrough | 45 Days | [11 empty] | Milestones
|  | Network Readiness | 30 Days | [11 empty] | Milestones
|  | IT / Modality Readiness | 15 Days | [12 empty] | Location Add | Equip Order | Phones | Card Readers |  | Network Equipment |  | RIS DocMWL / Fax
|  | TDR with End Users | 5 Days | [11 empty] | Incident Number
|  | Go-Live Issue Resolution | Week After | [19 empty] | Site Build
Site Blueprint
Product Owner | Quantity | Equipment Status | Items Ordered | Items Received |  | Modality Type | Connection Date | IP Address | Subnet | Gateway | DNS1 / DNS2 | Vendor | AE Title | DAS | MWL | Port | RITM Request | End to End Testing | Additional Note
Workstations | 5 | Desktops Bundle (with dual monitors) | FALSE | FALSE |  | CT | [11 empty] | FALSE
Workstations | 1 | Desktops Bundle (with single monitors) | FALSE | FALSE |  | MRI | [11 empty] | FALSE
Workstations | 1 | Laptop Bundle (with dual monitors and dock) | FALSE | FALSE |  | US | [11 empty] | FALSE
Workstations | 1 | Standard Monitors 24' | FALSE | FALSE |  | X-Ray | [11 empty] | FALSE
Workstations | 10 | Docking Station | FALSE | FALSE | [13 empty] | FALSE
Workstations | 2 | Reading Workstation | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | iPad | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | iPad MDM | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | Canon imageFORMULA DR-C225 II Office - document scanner | FALSE | FALSE |  | Existing Equipment |  | IP Address | Subnet | Gateway |  | Vendor | AE Title
Workstations |  | Jabra Evolve 40 UC stereo headset | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | Logitech HD Pro Webcam C920S | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | Topaz SignatureGem LCD1x5 - signature terminal - USB | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | Card Readers - Cody orders 3-6 weeks out | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | Dell CD Burner | FALSE | FALSE | [13 empty] | FALSE
Workstations | 0 | Desktop Printers | FALSE | FALSE | [13 empty] | FALSE
Workstations | 1 | MFP | FALSE | FALSE | [8 empty] | MFP Model |  |  |  |  | FALSE
Workstations | 9 | 1’ blue patch cables | FALSE | FALSE |  | MFP | [11 empty] | FALSE
Workstations |  | Cable Management - order Raceway and clips | FALSE | FALSE | [13 empty] | FALSE
Workstations | 3 | 1’ red patch cables | FALSE | FALSE | [13 empty] | FALSE
Workstations | 2 | 1’ yellow patch cables | FALSE | FALSE |  | RIS | Site to PACS | RIS | RIS | PACS | [5 empty] | Network Go-Live Date
Workstations | 1 | 3’ grey Cat 8 cable | FALSE | FALSE |  | Add Site Bin | Paperwork | Add Site¦ Org | Add New Users | Site Filter |  | TAX ID |  |  |  | IT Go-Live Date
Workstations | 1 | 5’ white Cat 8 cable | FALSE | FALSE | [7 empty] | Site Code |  |  |  | Site Go-Live Date
[5 empty] | Ordered | Installed | Turned Up |  |  |  |  | NPI |  |  |  | HL Complete | HL Tested |  | IP Address | Subnet | Gateway | DNS1 | DNS2
Infrastructure | 1 | Circuit/Fiber Primary | FALSE | FALSE | [7 empty] | Health Logix | [5 empty] | VLAN 300
Infrastructure | 1 | Circuit/Fiber Secondary | FALSE | FALSE |  |  |  |  | Network Equip Specifics |  |  | Obtained IP | [5 empty] | VLAN 303
Infrastructure | 1 | SDWAN Router - 7 days after Circuit Turned up | FALSE | FALSE | [7 empty] | Meet with Center Mgr Date
Infrastructure | 2 | Switch | FALSE | FALSE |  | FALSE | Pete |  |  |  |  | Software Validated |  |  |  | Specialty Hardware |  |  | Software List
Infrastructure | 3 | WAPs | FALSE | FALSE |  | FALSE | Pete/Josh/Anthony |  |  |  |  | RIS / PACS Type
Infrastructure |  | VPN (for remote modality connection) | FALSE | FALSE |  | FALSE | Pete
Infrastructure | 10 | Low voltage cabling/fiber | FALSE | FALSE |  | FALSE | Josh/Anthony
Infrastructure | 1 | UPS (rack mounted) | FALSE | FALSE |  | FALSE | FSO |  |  |  |  | E-Fax Date
Phones | 2 | phones | FALSE | FALSE |  | FALSE | Bron |  |  |  |  | Main Number | (254) 935-0415
Phones | 1 | ATA | FALSE | FALSE |  | FALSE | Bron |  |  |  |  | Inbound FAX
Fax | 1 | Go-Live of E-Fax |  |  |  |  | Bron

## Technical procurement tracker
SITE NAME : PROJECT NAME : IT Timeline | [14 empty] | Facility Name | FULL SITE NAME AS LISTED IN PUBLIC DIR
Site Address
|  |  |  | 120 | 100 | 80 | 60 | 40 | 30 | 20 | 10 | 5 | Go-Live | Post Go-Live | Center Manager
|  | TCO | 120 days | [12 empty] | date of | date of | date of | date of | date of | date of | date of | date of
|  | Permit / Circuit | 120 Days | [11 empty] | barriers
|  | Vendor Contract | 120 Days | [11 empty] | barriers
|  | Floor Plan, Equipment, Low Voltage | 100 Days | [11 empty] | barriers
|  | IP and Modality Info | 60 Days | [12 empty] | date of | date of | date of | date of | date of | date of | date of | date of
|  | Phone Plan | 60 Days | [11 empty] | Milestones | Suite Construction 4/27/26 | 7/23 MRI Delivery
|  | Site Walkthrough | 45 Days | [11 empty] | Milestones | Permit Approval 1/15/26 | 7/7 CT Delivery
|  | Network Readiness | 30 Days | [11 empty] | Milestones
|  | IT / Modality Readiness | 15 Days | [12 empty] | Location Add | Equip Order | Phones | Card Readers |  | Network Equipment |  | RIS DocMWL / Fax
|  | TDR with End Users | 5 Days | [11 empty] | Incident Number
|  | Go-Live Issue Resolution | Week After | [19 empty] | Site Build
Site Blueprint
Product Owner | Quantity | Equipment Status | Items Ordered | Items Received |  | Modality Type | Connection Date | IP Address | Subnet | Gateway | DNS1 / DNS2 | Vendor | AE Title | DAS | MWL | Port | RITM Request | End to End Testing | Additional Note
Workstations | 3 | Desktops Bundle (with dual monitors) | FALSE | FALSE |  | CT |  | 10.206.105.61 | 255.255.255.128 | 10.206.105.1 |  | Siemens GO UP 64 Slice | [5 empty] | FALSE
Workstations | 3 | Desktops Bundle (with single monitors) | FALSE | FALSE |  | MRI |  | 10.206.105.51 | 255.255.255.128 | 10.206.105.1 |  | Siemens SOLA 1.5T | [5 empty] | FALSE
Workstations | 1 | Laptop Bundle (with dual monitors and dock) | FALSE | FALSE |  | MRI Remote |  | 10.206.105.52 | 255.255.255.128 | 10.206.105.1 | [7 empty] | FALSE
Workstations | 0 | Standard Monitors 24' | FALSE | FALSE |  | MRI Bayer Injector |  | 10.206.105.53 | 255.255.255.128 | 10.206.105.1 | [7 empty] | FALSE
Workstations | 0 | Docking Station | FALSE | FALSE | [13 empty] | FALSE
Workstations | 0 | Reading Workstation | FALSE | FALSE | [13 empty] | FALSE | Permite Approved Site is still a shell Building construction start of suite is April 27th Site Possible Go- Live AUG 24th Power to Building Jul 12 IT Primary Circuit Jul 3 MRI Delivery Date 7/23/26 CT Delivery Date 7/7/26 Ultrasound Delivery Date 8/11/26 Construction End Aug 17/26
Workstations | 1 | iPad | FALSE | FALSE | [13 empty] | FALSE
Workstations | 1 | iPad MDM | FALSE | FALSE | [13 empty] | FALSE
Workstations | 7 | Canon imageFORMULA DR-C225 II Office - document scanner | FALSE | FALSE |  | Existing Equipment |  | IP Address | Subnet | Gateway |  | Vendor | AE Title
Workstations |  | Jabra Evolve 40 UC stereo headset | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | Logitech HD Pro Webcam C920S | FALSE | FALSE | [13 empty] | FALSE
Workstations |  | Topaz SignatureGem LCD1x5 - signature terminal - USB | FALSE | FALSE | [13 empty] | FALSE
Workstations | 2 | Card Readers - Cody orders 3-6 weeks out | FALSE | FALSE | [13 empty] | FALSE
Workstations | 6 | Dell CD Burner | FALSE | FALSE | [13 empty] | FALSE
Workstations | 0 | Desktop Printers | FALSE | FALSE | [13 empty] | FALSE
Workstations | 1 | MFP | FALSE | FALSE | [8 empty] | MFP Model |  |  |  |  | FALSE
Workstations | 10 | 1’ blue patch cables | FALSE | FALSE |  | MFP |  | 10.206.104.10 | 255.255.255.128 | 10.206.104.1 | [7 empty] | FALSE
Workstations | 10 | Cable Management - order Raceway and clips | FALSE | FALSE | [13 empty] | FALSE
Workstations | 4 | 1’ red patch cables | FALSE | FALSE | [13 empty] | FALSE
Workstations | 3 | 1’ yellow patch cables | FALSE | FALSE |  | RIS | Site to PACS | RIS | RIS | PACS | [5 empty] | Network Go-Live Date |  | 2026-07-23
Workstations | 1 | 3’ grey Cat 8 cable | FALSE | FALSE |  | Add Site Bin | Paperwork | Add Site¦ Org | Add New Users | Site Filter |  | TAX ID | xx-xxxxxxxx |  |  | IT Go-Live Date |  | 2026-08-10
Workstations | 10 | 5’ white Cat 8 cable | FALSE | FALSE | [7 empty] | Site Code | xxxxx |  |  | Site Go-Live Date |  | 2026-08-24
[5 empty] | Ordered | Installed | Turned Up |  |  |  |  | NPI | xxxxxxxxxx |  |  | HL Complete | HL Tested |  | IP Address | Subnet | Gateway | DNS1 | DNS2
Infrastructure | 1 | Circuit/Fiber Primary | FALSE | FALSE | 3/23/26 reminder | [6 empty] | Health Logix | [5 empty] | VLAN 300 | 10.206.104.0/25 | 255.255.255.128 | 10.206.104.1
Infrastructure | 1 | Circuit/Fiber Secondary | FALSE | FALSE |  |  |  |  | Network Equip Specifics |  |  | Obtained IP | [5 empty] | VLAN 303 | 10.206.105.0/25 | 255.255.255.128 | 10.206.105.1
Infrastructure | 1 | SDWAN Router - 7 days after Circuit Turned up | FALSE | FALSE | [7 empty] | Meet with Center Mgr Date
Infrastructure | 2 | Switch | FALSE | FALSE |  | FALSE | Network |  |  |  |  | Software Validated |  |  |  | Specialty Hardware |  |  | Software List
Infrastructure | 3 | WAPs | FALSE | FALSE |  | FALSE | Anthony |  |  |  |  | RIS / PACS Type |  | Fuji RIS/Intelerad PACS |  |  |  |  | AHI IMG Centers
Infrastructure |  | VPN (for remote modality connection) | FALSE | FALSE |  | FALSE | Network | [11 empty] | Dynasoft Print Driver
Infrastructure | 10 | Low voltage cabling/fiber | FALSE | FALSE |  | FALSE | Anthony | [11 empty] | Altamont 3.4
Infrastructure | 1 | UPS (rack mounted) | FALSE | FALSE |  | FALSE | FSO |  |  |  |  | E-Fax Date | [6 empty] | Clario
Phones | 8 | phones | FALSE | FALSE |  | FALSE | VOIP Engineer |  |  |  |  | Main Number | xxx-xxx-xxxx | [5 empty] | Vulkan shortcuts
Phones | 1 | ATA | FALSE | FALSE |  | FALSE | VOIP Engineer |  |  |  |  | Inbound FAX | xxx-xxx-xxxx | [5 empty] | Altamont shortcut
Fax | 1 | Go-Live of E-Fax |  |  |  |  | VOIP Engineer | [11 empty] | AHI PACS Synapse
zvext v4.4.2
AHI IMG Centers Manger
Batch Share Drive
permit approval 1/15

## NW & IT Checklist (at site)
Arrival
FALSE | 1. Verify building access via codes & keys with site manager
FALSE | 2. Verify contact number for Site Mgr / Site Admin
FALSE | 3. Verify current user accounts / access list with site manager (Global Pass, MI, Pacs, etc)
FALSE | 4. Verify all share folders and account access with site manager
FALSE | 5. Verify workstation placement onsite with site manager
FALSE | 6. Identify a good IT staging area
FALSE | 7. Verify Company equipment shipped to facility
FALSE | a) Network equipment: ie routers, switches, AP’s, cables, UPS
FALSE | b) Computers, Monitors, Peripherals, Scanners, CD drives, card readers, and Printers | Device | Port | To Device | Cable Color | Port on Switch
Network Steps |  | EPIK / FlexEdge | 0/0 | SDWAN | Grey | 01 on Flexedge / Epik
FALSE | 1. Verify Network is up ( connect laptop and pull an IP address ) | SD-WAN | 1 | WAN | White
FALSE | 2. Contact Network Engineer to verify on their end. | SD-WAN | 2 | Broadband | White
FALSE | 3. Update Go – Live Thread with progress on network connectivity. | SD-WAN | 3 | To Switch | Grey | port 48 / 47 on Switch
Staging / Preparation |  | Momentum CyberData | 1 | To Switch | Black | 47
FALSE | 1. Unbox and stage desktops, monitors, scanners and other peripherals. | Modality | NIC | To Switch | Red | 40-46
FALSE | 2. Unbox and stage printers | PC's | NIC | To Switch | Blue | Port 1 - 39
FALSE | 3. Coordinate with FSO to verify equipment locations. (if onsite) | AP's | NIC | To Switch | Yellow | Port 1 - 39
FALSE | 4. Connect all devices to wall ports, then from patch panel to switch. | UPS | 2 | To Switch | Black | Port 2
FALSE | 5. Verify network connectivity. | DATA+STATIC VLAN (300) /25 |  |  |  | Modality Subnet Allocations (VLAN 303) /25
FALSE | 6. Document all IP’s, Mac Addresses, Hostnames and locations of equipment | Description (Last Octet) | Start | End |  | Function / Modality | Last Octet
FALSE | 7. Test workstations by logging on and launching used applications. | Router | 1 | 1 |  | Gateway | x.x.x.1
FALSE | 8. Address cable management for workstations. | Reserved | 2 | 9 |  | Infrastructure/PACS Systems | .2-.10
Printer Preparation |  | Printers | 10 | 19 |  | Mammo (MG) | .11-.20
FALSE | 1. Gather printer IP address and Host Names (Printer IP Range .50 >) | Servers | 20 | 29 |  | Ultrasound (US) | .21-.30
FALSE | 2. Update Go – Live thread with list of printers to be added into Print Installer, Including the following | DHCP User Scope | 30 | 110 |  | Bone Density (BD) / Dexa (SR) | .31-.40
FALSE | A) Hostname: “site code” _ “printer location” (ex. ABCD _ Reception) | Reserved - do not use | 111 | 126 |  | X-Ray (CR) | .41-.50
FALSE | B) Make / Model of printer |  |  |  |  | MR | .51-.60
FALSE | C) IP Address |  |  |  |  | CT (PET CT) | .61-.70
FALSE | 3. Configure any Scan to Folder / Scan to Email settings. (if needed) |  |  |  |  | C-arm/Fluro | .71-.80
FALSE | A) Locate any file folder path along with Authentication username and password |  |  |  |  | Nuc Med | .71-.90
FALSE | B) Locate SMTP server address, port, and Authentication information. (If enabled) |  |  |  |  | Other Static (CD Burners, Paper Scanners) | .91-.100
IT Go-Live | [5 empty] | DHCP (Injectors, IOT Medical Devices) | .101-.126
FALSE | RITM to Business Apps for Scanner mapping with Individual PC names
FALSE | Software Validation with Center Manager(ensure it is working and the staff has access)
FALSE | Ensure Printers are labeled and in Intune / Print Logic as searchable device or manual mapping
FALSE | Validate Guest and Secured Wifi access and use
FALSE | Add TVs to Wifi

## TDR (at the site)
Technical Dress Rehearsal Check List
Item | Status | Date Completed | POC | Steps Needed
Circiut 1 | FALSE |  |  | Check Internet Access by Direct Connection to Granite Circiut to validate internet
Circiut 2 | FALSE |  |  | Connect to SDWAN the SDWAN to Switch validate
Switch | FALSE |  |  | Request Modality ports VLAN 303, reserve Printer Ips, Ping gateway and ping google 8.8.8.8
SDWAN / PaloAlto | FALSE |  |  | issues with webpage access and or Controller access work with Pete
ATA | FALSE |  |  | get dial tone from port 1 of ATA with analog phone, send and receive test fax
Phones | FALSE |  |  | Make and receive calls, park call and transfer
WAP | FALSE |  |  | Use Advanced IP scan for IP and MAC, connect with Putty push software via script to associate connect with controller. Use NetSpot to create Heatmap
Software Check | FALSE |  |  | Check if Software is aligned with Site Guide on Current Software list in Project Workbook, ensure end users have access
CT Modality Connection | FALSE |  |  | Get IP Information and MWL and DAS info on modality complete DICOM PING
MRI Modality Connection | FALSE |  |  | Get IP Information and MWL and DAS info on modality complete DICOM PING
Xray Modality Connection | FALSE |  |  | Get IP Information and MWL and DAS info on modality complete DICOM PING
US Modality Connection | FALSE |  |  | Get IP Information and MWL and DAS info on modality complete DICOM PING
CT Modality End to End Test | FALSE |  |  | Must include site Filter with order from RIS and received on MWL to send study to DAS and seen in RIS
MRI Modality End to End Test | FALSE |  |  | Must include site Filter with order from RIS and received on MWL to send study to DAS and seen in RIS
Xray Modality End to End Test | FALSE |  |  | Must include site Filter with order from RIS and received on MWL to send study to DAS and seen in RIS
US Modality End to End Test | FALSE |  |  | Must include site Filter with order from RIS and received on MWL to send study to DAS and seen in RIS
PACS Filter | FALSE |  |  | End Users need to have PACS Pilter for site verify with users
Printer | FALSE |  |  | Reserve IP with Pete, lable with Hostname changed to match facility and IP, connect on PCs, Connect SMTP for email access
Zscaler | FALSE |  |  | Must use US Radiology login for all MS Logins and SSO

## Go-Live Issues Tracker
Issue Tracker | Description | Next Steps | Date of Update | Details on Area | Go-Live +1 | Go-Live +2 | Go-Live +3 | Go-Live +4
Ledgend
Completed Issues mark green
Details on Area = Status
Go-Live + equals Days after GL
Issue Tracker = RITM / Summary
Lessons Learned